Written Solution Report

Sarvasya — Access for All

| Field | Details |
| --- | --- |
| Team Name | Code-Blooded |
| Institution Name | Drs. Kiran & Pallavi Patel Global University |
| Yi Chapter | Vadodara |
| City | Vadodara |
| Track | Accessibility |
| Problem Statement Title | Audit to Action |
| Solution Name | Sarvasya — Access for All |
| Team Members & Roles | Hetanshi Sidhpura (Project Administrator - Captain) Aaryan Jaiswal (Tech Lead) Dhruvi Jamnapara (Research) |
| Date of Chapter Level Round | 22nd August 2026 |

# 3.1 Problem Understanding [15 marks]

India has over 2.68 crore persons with disabilities (Census 2011); WHO estimates the true figure at 7–11 crore when invisible disabilities are included. The Rights of Persons with Disabilities (RPwD) Act 2016 mandates barrier-free access in all public buildings, yet an audit by NCPEDP found that less than 3% of government buildings are fully accessible (with essential places like courts and hospitals remaining out of reach).

The visible symptoms are steep ramps, missing lifts, absent tactile paths, and non-compliant restrooms. However, the root systemic gaps are:

1.  Zero transparency and accountability: No publicly accessible, real-time database tracks building compliance before citizens visit or holds officials accountable.

2.  Absence of a structured complaint-to-resolution pipeline: Complaints are left un-actioned or dismissed without valid justification. Crucially, post-construction retrofitting (e.g., adding a handrail when a lift is fundamentally missing) cannot fix structural access failures. The pipeline must focus on stopping future permissions for non-compliant designs at the planning stage — rejection of non-compliant designs is the primary goal.

3.  No incentive for compliance: Builders currently gain a competitive advantage by skipping accessibility to reduce construction costs and maximize sellable "carpet space." Existing fines (e.g., ₹5 lakh) are negligible developer expenses. The cost of non-compliance must be made significantly higher than compliance through delayed occupancy certificates, frozen planning approvals, and institutional sanctions.

4.  Fragmented enforcement: Accountability is split between architects, contractors, and municipal bodies, so no single entity owns the failure.

The core problem is the lack of accountability and information transparency, treating accessibility as a paper formality rather than a lived reality.

# 3.2 Proposed Solution [25 marks]

Solution Name: Sarvasya — Access for All

One-line Description: A public civic platform that enforces building accessibility by tracking compliance against IS 4963, publishing Live Accessible Facility Status, providing sign-reading & navigation tools, and holding planning authorities legally accountable.

Solution Type: ☑ Product · ☑ Technology · ☑ Platform · ☑ Service · ☐ Hardware · ☑ Hybrid

MVP Format: Website (offline-capable) · Full Product Roadmap: Native mobile app

## Core Features

Sarvasya addresses accessibility across interconnected operational layers, prioritizing dignified independent access over charitable assistance:

### Layer 1 — Live Accessible Facility Status & Audit Registry

Replaces meaningless 1–5 abstract numerical ratings with a Live Accessible Facility Status Panel. An Accessible Facility is defined as a complete set of prerequisite accessibility features correctly implemented. Key facilities tracked include:

•  Accessible Ramp (slope, width, surface)

•  Accessible Toilet (turning radius, grab rails, door swing)

•  Accessible Lift (door width, braille buttons, audio feedback)

•  Accessible Stairs (handrails on both sides, tactile warning)

•  Accessible Parking (reserved space, signage, level path)

•  Accessible Service Counter (lowered height, knee space)

Each building record displays Y/N status per facility, compliance gap reports referenced against IS 4963 (the updated BIS standard superseding NBC 2016), verified audit summaries, and indoor wayfinding maps. Independent verification is achieved through audit pairs comprising architecture/civil engineering students paired with PwD auditors.

### Layer 2 — Accountable Complaint Pipeline & Institutional Penalties

Citizens file complaints that enter a transparent, shipping-tracker-style pipeline: Submitted → Assigned to Technical Officer (Name Visible) → In Progress → Resolved / Dismissed.

•  Dismissal Rights & Appeals: Officers must provide mandatory written justification for dismissals, and complaints cannot be dismissed without giving complainants an opportunity to appeal.

•  Institutional Sanctions: If a municipal ward or planning department accumulates >10 unresolved complaints, the department itself is automatically flagged for an SOP audit to justify its enforcement procedures.

•  Developer Accountability & Capacity Building: Identifies and calls to account officers and developers who facilitated non-compliant builds, providing mandatory capacity-building training.

•  Submission Integrity & 2FA: Deter misuse using 2FA user verification and a mandatory tick-box declaration of intent before filing: "To the best of my ability, I declare that what I am submitting is true."

### Layer 3 — Assistive Tech & Universal Accessibility Controls

Focuses on tools for dignified independent navigation: Voice Command Mode with an automated sign-board reader that reads signage aloud for visually impaired users. Features variable text size (A-, A, A+), high-contrast, color inversion, colorblind-safe themes (Deuteranopia/Tritanopia), ARIA labels, semantic HTML, and offline-first architecture via localStorage.

Design Rationale: Charitable "buddy" tracking and volunteer dependency features have been deliberately excluded to uphold independent, dignified access. Accessibility is an enforceable legal right, not a charitable favor.

## Root Cause → Solution Mapping

| Root Cause (from 3.1) | Sarvasya’s Response |
| --- | --- |
| No transparency | Live Accessible Facility Status registry with IS 4963 compliance audit trails |
| No complaint accountability | Shipping-tracker pipeline with named technical officers, mandatory appeal process, and department-level sanctions |
| Unenforceable design standards | Developer accountability, planning department SOP audits, and design-stage submission checklists |
| No compliance incentive | Delays in occupancy certificates & public facility status create financial and reputational pressure |

## Target Users & Beneficiaries

•  Primary Users (PwD): Persons with mobility, visual, and cognitive impairments who gain dignified, independent access.

•  Universal Beneficiaries (Everyone): Regular users benefit daily — delivery agents carrying packages (lever handles vs knobs), parents with strollers (ramps & spacious lifts), children (accessible door latches), and elderly citizens.

•  Infrequent & Emergency Users: Emergency responders moving stretchers, furniture movers, and fire evacuation teams operating in accessible infrastructure.

•  Institutional Stakeholders: Urban Planning & Town Planning Departments, Public Works Department (PWD), Municipal Technical Officers, Architects, and Builders.

# 3.3 Policy Recommendation [feeds Solution Quality & Impact Potential]

Policy Gap: The RPwD Act 2016 mandates accessibility, and IS 4963 outlines technical specifications. However, municipal planning websites lack a mandatory pre-construction submission checklist for accessibility facilities, allowing non-compliant designs to pass blue-printing and receive building permits.

Specific Policy Recommendation:

Mandatory Digital Accessibility Checklist & Public Disclosure:

1.  The Municipal Planning & Town Planning Department must integrate a mandatory Accessibility Facility Checklist on their developer planning submission portal. No building permit or Occupancy Certificate shall be issued without digital verification against IS 4963 standards.

2.  Every public building must publish its Live Accessible Facility Status on a centralized register updated within 30 days of any audit or material resolution. Non-publication or false declaration shall trigger planning department sanctions.

Which Government Body Should Act:

•  Primary: Municipal Corporation Urban Planning & Town Planning Departments, Public Works Department (PWD)

•  Supporting: MoHUA & State Urban Development Departments (building code enforcement)

•  Implementation: Municipal Technical Officers and Certified Universal Design Auditors

# 3.4 Feasibility & Scalability [20 marks]

## First 90 Days (Pilot Implementation in Vadodara)

| Days | Milestone |
| --- | --- |
| 1–15 | Deploy pilot in Vadodara (Ward 6 — Alkapuri / Akota). Onboard 10 public buildings, 3 partner NGOs (Enable Me Access, Accessible Vadodara, United Way), and 1 Municipal Technical Accessibility Officer (Civil/Urban Planning background). |
| 16–30 | Conduct on-ground accessibility audits using audit pairs (architecture/civil engineering students paired with PwD auditors from local NGOs). Populate Live Accessible Facility Status and wayfinding maps. |
| 31–50 | Launch public-facing platform with pilot data. Distribute QR-coded posters at building entrances. Onboard 50 citizen testers (including wheelchair users, visually impaired individuals, and civil engineering students). |
| 51–75 | Expand Complaint Resolution & Enforcement Workflow: Collect complaint pipeline data, train 2 municipal technical officers on complaint verification, establish appeal processing procedures, and iterate on assistive sign-reader features based on user feedback. |
| 76–90 | Publish pilot impact report (buildings audited, material resolutions achieved, average resolution time, department SOP compliance). Prepare proposal for city-wide rollout across Vadodara. |

## Cost Estimate (Pilot)

| Item | Cost (INR) |
| --- | --- |
| Cloud hosting (1 year) | ₹36,000 |
| Audit kits × 5 (measuring tape, inclinometer, clipboard) | ₹5,000 |
| QR posters & printed awareness material | ₹8,000 |
| Travel & field expenses (pilot ward, 90 days) | ₹15,000 |
| Student auditor stipends (3 × ₹3,000/mo × 3 mo) | ₹27,000 |
| Miscellaneous (SIM data packs, printing, contingency) | ₹9,000 |
| Total Pilot Cost | ₹1,00,000 (approx.) |

Built on open-source tools (React, Vite, Express) — zero licensing costs. The MVP website already runs offline.

## Infrastructure, Partners & Stakeholders

•  Infrastructure: Laptop, internet connection, ₹3,000/year cloud server. (App operates offline).

•  Target Partner NGOs:

◦  Enable Me Access — Technical accessibility expertise; only NGO with an active local chapter in Vadodara/Gujarat.

◦  Accessible Vadodara — PwD community representation.

◦  United Way Vadodara — Strong local influence & outreach.

Key Stakeholders & Roles:

| Stakeholder | Role |
| --- | --- |
| Urban Planning / Town Planning / PWD | Enforce submission checklists, review >10 complaint ward flags, validate permits |
| Municipal Technical Officer | Validates audit results, processes complaints, handles appeals |
| Enable Me Access & Local NGOs | Field audit oversight, recruiting PwD student audit partners |
| Architecture & Engineering Students + PwDs | Conduct independent field audits as verified audit pairs |
| Architects / Builders | Complete mandatory pre-construction accessibility checklist before submission |
| Yi Vadodara Chapter | Coordinate pilot execution and community outreach |

## Scalability Roadmap

Pilot (1 Ward, 10 buildings in Vadodara) → 90 days → City (Vadodara city-wide, 100+ buildings) → 6 months → State (Gujarat urban centers, 1,000+ buildings, state urban development integration) → 12 months → National (10,000+ buildings, MoHUA API integration) → 24 months.

# 3.5 Innovation & Differentiation [15 marks]

Most accessibility efforts in India are report-based — an NGO audits a building, files a paper report, and it gathers dust. Sarvasya inverts this model by making accessibility data live, public, and actionable.

| Existing Effort | Gap | Sarvasya’s Advantage |
| --- | --- | --- |
| Sugamya Bharat Abhiyan | Top-down, no citizen feedback loop, no public facility status | Bottom-up citizen reporting + public transparency + IS 4963 audit trails |
| Wheelmap.org | Wheelchair-only; no compliance data or legal complaint pipeline | Full Accessible Facility status (Toilets, Ramps, Lifts, Parking, Stairs) against IS 4963 |
| AccessNow | Crowdsourced reviews only; no officer accountability | Named technical officer assignment, complainant appeal rights, and department-level sanctions |
| Manual CPWD audits | Paper-based, no public disclosure, no follow-up | Digital audit trail, Realtime Accessible Facility Status, indoor sign-reading |

Core Innovation: The complaint-to-accessibility status & accountability feedback loop. Unresolved complaints directly impact a building’s public accessibility status, while triggering planning department SOP reviews after threshold violations (>10 complaints). This creates systemic pressure at the planning permit level rather than relying on post-construction goodwill.

# 3.6 Impact Potential [15 marks]

Direct Beneficiaries: India’s 2.68 crore registered PwDs plus an estimated 4–8 crore unregistered individuals. In Vadodara (~22+ lakh population), approximately 1–1.8 lakh persons with disabilities benefit directly.

Universal Beneficiaries: ~13.8 crore elderly citizens, parents with strollers, delivery workers, pregnant women, and emergency responders who rely on universal design infrastructure.

## Measurable KPIs (Year 1 Pilot)

| KPI | Target (Year 1 Pilot) |
| --- | --- |
| Live Accessibility Status posted | 100+ buildings |
| Accessibility complaints filed | 500+ |
| Average complaint time to Material Resolution | < 30 days |
| Average complaint resolution time to Legal Accountability | < 60 days |
| Complaints resolved vs. dismissed ratio | > 70% resolved (with appeal option) |
| Student-PwD Universal Design Audit Pairs active | 25 pairs |
| Emergency & sign-reader uses | Tracked |
| User satisfaction (post-visit survey) | > 80% positive |

## Timeline to Impact

•  30 days: First buildings in Vadodara display Live Accessible Facility Status; initial complaints logged.

•  90 days: Measurable material resolution data; municipal technical officers actively processing appeals and audits.

•  6 months: Demonstrable building compliance improvements in Vadodara Ward 6 driven by design submission checklists and status transparency.

•  12 months: City-level data ready for Gujarat State Urban Development Department policy integration.

Sarvasya shifts accessibility from a charitable after-thought into an enforceable structural standard.

All feedback comments and highlighted annotations from reviewer Peter Gibson have been incorporated into this document.